## Technical
| HOURS | Technical - changes to be made
1 |  | Under "service provider", list of creditors to be available as a drop down menu
2 | 1 | Under reactive maintainance, jobcard function to be added, same as preventive
this came later after I was done with the SRS which was still in consideration.
3 | 2 | Parts requisition, which is currently under deactive maintainance is to be a tab on its own below the reactive & preventive tabs as it can be requested by both
I was adviced by bBett verbally to do like this. A refernce of rkkb site was given and was told to replicate
4 | 0.25 | JOB CARDS - | On Job card - spell chack - "SESLECT VEHICLE"?
5 |  |  | Under job category, entire tab to be removed - makes no sense
Kindly clarify - This means on job card, remove job category altogether - we do not need the category - what was it intended to do?
6 |  |  | Job type to be modifiable - to be presented as a udf
Kindly clarify The client is to enter their own wordings in the dropdown in this tab
7 |  |  | Service type - this has nothing - can it be amended? To have service typoe a, b, c, d
A NEW SERVICE TYPE CAN BE ADDED FROM SETTINGS
8 |  |  | Upload of service type sheet to be enabled
Kindly clarify Client wants to import his own PDF sheet or a checklist - both options to be availed on this tab
9 |  |  | "Assigned to" - this is to be connected to HR - so that HOD can assign the same to someone - Bett to advice
THIS FEATURE EXISTS
10 | 0.5 |  | Previous KM reading - to pick from previous readin - upon setup, to enter first reading - possible?
11 |  |  | Periodic service notification is available how? - is there a prompt for this?
THIS FEATURE EXISTS. An email is send at the time assigning the vehicle
12 |  |  | Actual kms covered - to be a formula - (current minus previous)
THIS FEATURE EXISTS
13 | 3 |  | Fuel balance to have a drop dowm - full, 3/4th, 1/2, 1/4, close to empty
new requirement. Not found in SRS. Neither was told by Bett
14 |  |  | Imspections - list to be extended
THIS FEATURE EXISTS
15 |  |  | What is the tab links at the bottom
Kindly clarify
16 |  | Job card similar as above to be availed for both reactive and preventive
17 |  | Parts requisiion - | Parts requisition - makes no sense - greyed out tabs etc etc
THIS FEATURE EXISTS
18 |  |  | Is parts requisition linked to inventory on sage??
19 |  |  | Vehicle number is greyed out - what do we do with this?
a jobcard is linked to a vehicle. Once a Job Card is created,the vehicle remains locked and can't be changed else there is not traceability of Jobcard.
20 | 4 |  | When on clicking update, what happens - does this hit inventory? Who gets the prompt? - are alerts sent out? - is this module linked to anything as of now?
It is only picking the values / data from SAGE. It is not updating SAGE inventory. I was told to do so, but it is incomplete. It is neither sending any notification to anyone nor sending any email.
21 |  |  | When clicking on "spare", dropdown is to have all stocks available as a dropdown search field
THIS FEATURE EXISTS. All items are being picked from SAGE.
22 |  |  | After processing parts requisition, does the same appear in the job card? Can we see?
THIS FEATURE EXISTS. All items are being listed in the Job Card and greyed out so no editing could be done
23 | 2 |  | Layout and formats are shoddy - see parts requision screen
Agreed. A format could be provided and this will be customised to that
24 | 4 |  | We need a user manual done up for this entire process
I was not advised to work on User Manual.
25 |  | Fuelling - | Registration number not there in entore list and schedule
This Feature Exists
26 | 1 |  | Provider to be linked to creditor from sage for entire application
I was advised that this information would be entered from Settings.
27 | 2 |  | Throughout technical,. Km readings, to have a dropdown list with miles, kilometres, and hours
This is new requirement. Its neither there in SRS nor was advised to me.
28 |  |  | Throughout technical and all applications, wherever a user is selected, the same has to be linked to HR
I was advised to fetch this list from SAGE.
29 |  |  | On fuelling list, kilometres when fuelled has to be viewed on this report
Need further clarifications
30 | 2 | Hiring assets - | asset list to be provided and imported
Will be imported.
31 |  |  | What does tonnes under hiring assets mean or refer to????
I was advised that the Hiring amount depends on the Tonnage of Asset. Hence the field was provided
32 | 1 |  | Under hioring from - how can this be a client? This has to be a supplier linked from sage
Noted. It will be fixed.
33 |  |  | There also has to be a sxcreen for hiring to", where the customer list is linked from sage
This exists. If title needs to be changed then please advise.
34 | 0.1 |  | The title is "hire assets form"? - to be hire assets from and hire assets to
Does this need to be changed to "Hire Assets From and To" Please advise.
35 |  |  | Link between technical module and sage for financial impact and all documemts to be very clearly explained
36 |  |  | Eg - job card or hiring assets from or to forms
Kindly explain if you want this to be in form of a Guide or what ?
37 |  | Reports | Maintainance reports - where are the preventive maintainance reports, monthly report
38 | 4 | Full list of reports - these are not available???? Can we see these on the system and well tested and working
39 |  |  | Mileage - kms between service and fuel entered in litres between service to be divided and mileage obtained
Please advise if this take higher priority over Checklist module as I am working on that one
26.85

## Sheet1
1 | Under "service provider", list of creditors to be available as a drop down menu